## Sheet1
System Name | LuxStay Properties Rental Management System
Members: | Christian Hans Israel E. Paras | A
| Marc Andre C. Dotarot | B
| Feerdee Anne C. Llaban | C
Statuses |  | Todo
In-Progress
Done
On-hold
[6 empty] | August |  |  |  | September |  |  |  | October
Tasks | Assignee | Date Started | Target Date | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Initial Phase
1.1 Create Functional Requirements Document | A, B, C | 2024-08-21 | 2024-08-24 | 2024-08-24 | Done
1.2 Create Gantt Chart | A, B, C | 2024-08-22 | 2024-08-30 | 2024-08-30 | Done
2. FIRST CHECKPOINT (HALF)
2.1 Create GitHub Repository | A | 9/23/24 | 9/23/24 | 9/23/24 | Done
2.2 Commit Functional Requirement and Gantt Chart | A | 9/23/24 | 9/23/24 | 9/23/24 | Done
3. FIRST CHECKPOINT (FULL)
3.1 Assign functionalities | A, B, C | 9/23/24 | 9/23/24 | 9/23/24 | Done
3.2 Create Create ERD using VisualParadigm | A, B, C | 9/23/24 | 9/28/24 |  | In-Progress
3.3 Commit ERD | A, B, C | 9/23/24 | 10/13/24 |  | On-hold
3.4 Commit UI/UX design (each) | A, B, C | 9/23/24 | 10/13/24 |  | On-hold